## Sheet2
Yearly Plan
Year | Major Objective
2024 | Achieve compliance with CIS baseline items
Quarterly Plan |  | Goals
Q1 | Implement Role-Based Access Control (RBAC) | Define roles and assign permissions.
Q2 | Enhance Network Security | Set up NSGs and configure firewall rules.
Q3 | Improve Monitoring and Logging | Deploy Azure Monitor and Log Analytics.
Q4 | Conduct Security Assessment | Perform vulnerability scanning and audits.
Week | Component | Deliverable | Estimated Time (Hours) | Difficulty Level (1-5)
2024-10-01 | RBAC Implementation | Define user roles and permissions | 10 | 3
2024-10-08 | RBAC Implementation | Assign roles to users in Azure | 5 | 2
2024-10-15 | Network Security | Set up Network Security Groups (NSGs) | 8 | 4
2024-10-22 | Network Security | Configure inbound and outbound rules | 6 | 3
2024-10-29 | Monitoring and Logging | Deploy Azure Monitor | 7 | 3
2024-11-05 | Monitoring and Logging | Configure Log Analytics workspace | 5 | 2
2024-11-12 | Security Assessment | Schedule vulnerability scans | 3 | 2
2024-11-19 | Security Assessment | Review security policies and compliance requirements | 4 | 3
2024-11-26 | Security Assessment | Conduct a risk assessment | 6 | 4
2024-12-03 | Security Awareness Training | Develop training materials for staff | 5 | 2
2024-12-10 | Security Awareness Training | Conduct training sessions for users | 8 | 3
2024-12-17 | Review and Adjust | Review overall security posture and make adjustments | 4 | 3
| Goals | Goals